## Monthly Plan
Organization Chart Project - Monthly Plan
Week | Date Range | Task | Deliverable | Points | Status
Week 1 | 10.4 - 12.4 | Read requirements document | Understanding of project scope
|  | Study composite design pattern (Wikipedia) | Notes on pattern structure
|  | Draw UML class diagram (draw.io) | UML diagram for report
|  | Set up IntelliJ project with package | Project structure ready
|  | Create Component abstract class | Component.java
|  | Create Worker class (leaf) | Worker.java
|  | Create Group class (composite) | Group.java
|  | Implement menu UI (Point 1) | Menu loop working, q/Q quits | 1p
Week 2 | 13.4 - 19.4 | Build hard coded organization | OrganizationManager.java
|  | Implement print with indentation (Point 2) | Option 1 prints org correctly | 2p
|  | Test point 1 and 2 | Screenshots for report
|  | Implement add person feature (Point 3) | Option 2 working | 3p
|  | Test adding person to different groups | Screenshots for report
|  | Implement remove person feature (Point 4) | Option 3 working | 4p
|  | Test removing, empty group case | Screenshots for report
Week 3 | 20.4 - 26.4 | Create custom exception classes | 5 exception classes
|  | Add error handling to all operations (Point 5) | All error cases handled | 5p
|  | Test all error scenarios | Screenshots for report
|  | Write report: design section | UML + explanation
|  | Write report: testing section | Screenshots + descriptions
|  | Write report: analysis section | Learnings, difficulties
|  | Add source code to appendix | All .java files in report
Week 4 | 27.4 - 05.05 | Final testing of everything | Full test run
|  | Finalize report | Complete report document
|  | Export project zip from IntelliJ | Zip file ready
|  | Submit to Moodle | Report + code submitted

## Work Hours
Work Hours Log - Organization Chart Project
Date | Hours | Description | Point Level
2026-04-10 | 1 | Read project requirements, studied composite pattern wiki
2026-04-11 | 1.5 | Drew UML class diagram on draw.io
2026-04-12 | 0.5 | Planned class structure, figured out what methods needed
2026-04-13 | 1 | Set up IntelliJ project, created package structure
2026-04-16 | 2 | Coded Component, Worker, Group classes
2026-04-17 | 1.5 | Made menu loop, tested quitting with q and Q | 1p
2026-04-18 | 2 | Built hard coded organization in OrganizationManager
2026-04-19 | 1.5 | Implemented print with indentation, debugged spacing | 2p
2026-04-20 | 0.75 | Tested option 1, took screenshots
2026-04-21 | 2 | Implemented add person (option 2), findGroup method
2026-04-22 | 1 | Tested adding to different groups, took screenshots | 3p
2026-04-23 | 1.5 | Implemented remove person (option 3), removeWorker method
2026-04-24 | 1 | Tested removing, checked empty group works | 4p
2026-04-26 | 1.5 | Created 5 custom exception classes
2026-04-27 | 2.5 | Added try-catch to all operations, name validation
2026-04-28 | 1.5 | Tested all error cases, fixed edge cases | 5p
2026-04-29 | 2 | Started writing report, design section with UML
2026-04-30 | 1.5 | Report testing section, added screenshots
2026-05-01 | 1 | Report analysis section, added source code appendix
2026-05-02 | 1 | Final testing run, everything works
2026-05-04 | 1.5 | Finalized report, exported project zip
2026-05-05 | 0.5 | Submitted to Moodle
TOTAL HOURS | 30.25

## Summary
Project Summary
Phase | Est. Hours | Description
Planning & Design | 3 | Requirements, UML, pattern study
Point 1 - Menu | 1.5 | Menu UI, loop, quit
Point 2 - Print org | 3.5 | Hard coded org, print with indent
Point 3 - Add person | 3 | Add worker to group
Point 4 - Remove person | 2.5 | Remove worker, empty group
Point 5 - Exceptions | 5.5 | Error handling, validation
Report writing | 4.5 | Design, testing, analysis sections
Final testing & submit | 3 | Full test, export, submit
TOTAL | 26.5